## Sheet1
Week | Task | Assignee/s | Status | Remaining User Stories | In-Progress User Stories | Finished User Stories(IDEALLY)
Week 6 | Brainstorm to figure out more user stories | Liu Han | Finished | User Stories 1 | User Stories 5 --- Keep Track of User location | User Stories 5 --- Keep Track of User location
| UI Design | ChengYuan Cheng | Finished | User Stories 2 | User Stories 6 --- Limit Google Maps Area | User Stories 10 --- Separate the MTS and SD shuttle Activities pages
| Set up Google Maps activity page | Elyas, Liu Han | Finished | User Stories 3 | User Stories 9 --- UI Design
| Summary weekly meeting | Siraj Ghouse | Finished | User Stories 4 | User Stories 10 --- Separate the MTS and SD shuttle Activities pages
| Limit Google Maps to the county of San Diego | Elyas, Liu Han | Unfinished | User Stories 7
| Test the MTS functionality | Min Chang Kim | Finished | User Stories 8
| Continue working on MTS functionality | Eric Chen | Finished | User Stories 11
| Enable search for a destination functionality in Gmap | Liu Han, Eric Chen | Finished
| Enable google maps to keep track of user current location | Min Chang Kim, Siraj Ghouse | Finished
Week 7 | Feedback from clients | All members | Finished | User Stories 2 | User Stories 1 --- Select a bus stop and told when to leave | User Stories 5 --- Keep Track of User location
| Functionality(Enter a bus stop number) | Eric Chen, Min Chang Kim | Finished | User Stories 3 | User Stories 4 --- Set alert time | User Stories 6 --- Limit Google Maps Area
| Enable alert functionality | ChengYuan Cheng | In-Progress | User Stories 7 | User Stories 11 --- Capture live time of UCSD shuttle | User Stories 9 --- UI Design
| Update User Stories and Timeline | Liu Han | Finished | User Stories 8 | User Stories 9 --- UI Design | User Stories 10 --- Separate the MTS and SD shuttle
| Summary weekly meeting | Siraj Ghouse | In-Progress
| Test and merge codes | Min Chang Kim, Elyas | Finished
| Finish UI Design | ChengYuan Cheng | Finished
| Capture UCSD shuttle live time | Liu Han, Siraj Ghouse | In-Progress
Week 8 | Feedback from clients | All members |  | User Stories 2 | User Stories 1 --- Select a bus stop and told when to leave | User Stories 5 --- Keep Track of User location
| Update User Stories and Timeline | Liu Han |  | User Stories 7 | User Stories 3 --- Alert actually work | User Stories 6 --- Limit Google Maps Area
| Summary weekly meeting | Siraj Ghouse |  | User Stories 8 | User Stories 11 --- Capture live time of UCSD shuttle | User Stories 9 --- UI Design
| Functionality(select bus stop and told when too leave) ---- Continued working | Eric Chen, Min Chang Kim |  |  |  | User Stories 10 --- Separate the MTS and SD shuttle
| Finish alert functionality | ChengYuan Cheng |  |  |  | User Stories 4 --- Set alert time
| Test and merge codes | Min Chang Kim, Elyas
| Capture UCSD shuttle live time ---- Continued working | Liu Han, Siraj Ghouse
Week 9 | Feedback from clients | All members |  |  | User Stories 2 --- Input a destination and be told when to leave | User Stories 5 --- Keep Track of User location
| Update User Stories and Timeline | Liu Han |  |  | User Stories 7 --- Capture live feeds | User Stories 6 --- Limit Google Maps Area
| Summary weekly meeting | Siraj Ghouse |  |  | User Stories 8 ---- Waiting time of line at bus stop | User Stories 9 --- UI Design
| Combine all functionality of MTS ans SD shuttle | Elyas,ChengYuan Cheng |  |  |  | User Stories 10 --- Separate the MTS and SD shuttle
| Functionality(Input a destination and be told when to leave) | ChengYuan Cheng, Eric Chen |  |  |  | User Stories 4 --- Set alert time
| Capture live feeds for buses | Liu Han, Min Chang Kim |  |  |  | User Stories 1 --- Select a bus stop and told when to leave
| Figure out how to get waiting time of line | Elyas, Siraj Ghouse |  |  |  | User Stories 3 --- Alert actually work
User Stories 11 --- Capture live time of UCSD shuttle
Week 10 | Feedback from clients | All members |  |  | User Stories 8 ---- Waiting time of line at bus stop | User Stories 5 --- Keep Track of User location
| Enable functionality of getting waiting time of line | All members |  |  |  | User Stories 6 --- Limit Google Maps Area
| Update User Stories and Timeline | Liu Han |  |  |  | User Stories 9 --- UI Design
| Summary weekly meeting | Siraj Ghouse |  |  |  | User Stories 10 --- Separate the MTS and SD shuttle
User Stories 4 --- Set alert time
User Stories 1 --- Select a bus stop and told when to leave
User Stories 3 --- Alert actually work
User Stories 11 --- Capture live time of UCSD shuttle
User Stories 2 --- Input a destination and be told when to leave
User Stories 7 --- Capture live feeds
At the End of Week 10 | Deliver Final APP